## Timeline Tracker
Guardrail & Evaluation Layer — Build Tracker (Project 1, v3)
Total Tasks | -12 | % Complete | -100%
Done | 12
In Progress | 0
# | Phase | Task | Target Duration | Status | Benchmark / Done-When | Notes
1 | 1a — Trace Skeleton (Wk 1–4) | Design canonical trace schema | Week 1 | Done
2 | 1a — Trace Skeleton (Wk 1–4) | Build LangGraph adapter | Week 1–2 | Done
3 | 1a — Trace Skeleton (Wk 1–4) | Set up Postgres trace store | Week 2 | Done
4 | 1a — Trace Skeleton (Wk 1–4) | Build privacy/redaction filter | Week 2–3 | Done
5 | 1a — Trace Skeleton (Wk 1–4) | Build provider abstraction layer | Week 3 | Done
6 | 1a — Trace Skeleton (Wk 1–4) | Build mock evaluator | Week 3 | Done
7 | 1a — Trace Skeleton (Wk 1–4) | Implement caching layer | Week 3–4 | Done
8 | 1a — Trace Skeleton (Wk 1–4) | Implement retry / rate-limit handling | Week 4 | Done
9 | 1a — Trace Skeleton (Wk 1–4) | Benchmark: 10 known runs round-trip, zero data loss | Week 4 | Done | Zero data loss on round-trip
10 | 1a — Trace Skeleton (Wk 1–4) | Benchmark: secrets/PII confirmed redacted | Week 4 | Done | No unredacted secrets in stored traces
11 | 1a — Trace Skeleton (Wk 1–4) | Benchmark: repeated call served from cache | Week 4 | Done | Identical call not re-sent to provider
12 | Integration Check 1 | Verify trace schema covers all downstream fields | ~1 day | Done | Every field 1b–1d needs is present
13 | 1b — Basic Evaluation (Wk 5–6) | Build eval-signal schema (incl. evaluator_version) | Week 5 | Not Started
14 | 1b — Basic Evaluation (Wk 5–6) | Build rule-based evaluators | Week 5 | Not Started
15 | 1b — Basic Evaluation (Wk 5–6) | Build embedding evaluators | Week 5–6 | Not Started
16 | 1b — Basic Evaluation (Wk 5–6) | Build dataset versioning | Week 6 | Not Started
17 | 1b — Basic Evaluation (Wk 5–6) | Create 20–30 case hand-labeled dataset | Week 6 | Not Started
18 | 1b — Basic Evaluation (Wk 5–6) | Benchmark: rule-based checks match expected pass/fail | Week 6 | Not Started | Exact match vs. hand-labeled set
19 | 1b — Basic Evaluation (Wk 5–6) | Benchmark: embedding scores correlate with human judgment | Week 6 | Not Started | Directional correlation confirmed
20 | 1c — Groundedness (Wk 7–9) | Build claim extraction step | Week 7 | Not Started
21 | 1c — Groundedness (Wk 7–9) | Build evidence retrieval step | Week 7–8 | Not Started
22 | 1c — Groundedness (Wk 7–9) | Build entailment check step | Week 8 | Not Started
23 | 1c — Groundedness (Wk 7–9) | Implement full metric set (claims, unsupported, contradicted, coverage, retrieval failure, extraction confidence) | Week 8–9 | Not Started
24 | 1c — Groundedness (Wk 7–9) | Create labeled claim-level benchmark set | Week 9 | Not Started
25 | 1c — Groundedness (Wk 7–9) | Benchmark: entailment labels match human labels ≥ 80% | Week 9 | Not Started | ≥80% agreement with human labels
26 | Integration Check 2 | Verify groundedness results flow into eval-signal schema | ~1 day | Not Started | Evidence + severity populated correctly
27 | 1d — Security Suite (Wk 10–12) | Build prompt injection test module | Week 10 | Not Started
28 | 1d — Security Suite (Wk 10–12) | Build indirect injection test module | Week 10 | Not Started
29 | 1d — Security Suite (Wk 10–12) | Build permission / allow-list evaluation | Week 11 | Not Started
30 | 1d — Security Suite (Wk 10–12) | Build tool-argument validation | Week 11 | Not Started
31 | 1d — Security Suite (Wk 10–12) | Build loop / excessive-retry detection | Week 11 | Not Started
32 | 1d — Security Suite (Wk 10–12) | Build versioned security payload registry | Week 12 | Not Started
33 | 1d — Security Suite (Wk 10–12) | Benchmark: adversarial suite catch-rate meets threshold | Week 12 | Not Started | Defined min. % of payloads caught
34 | 1e — Dashboard (Wk 13–14) | Build dashboard UI skeleton | Week 13 | Not Started
35 | 1e — Dashboard (Wk 13–14) | Wire eval signals with evidence & severity | Week 13 | Not Started
36 | 1e — Dashboard (Wk 13–14) | Wire security findings view | Week 14 | Not Started
37 | 1e — Dashboard (Wk 13–14) | Benchmark: every finding traceable to trace_span_ids | Week 14 | Not Started | Manual walkthrough passes
38 | Buffer (Wk 15–16) | Debugging & polish | Week 15 | Not Started
39 | Buffer (Wk 15–16) | Documentation | Week 15–16 | Not Started
40 | Buffer (Wk 15–16) | Report / viva prep | Week 16 | Not Started